| ID | Risk | Category | L | I | Score | Rating | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Regulatory approval for online Rx sales delayed or denied | Regulatory | 4 | 5 | 20 | Critical | Early regulator engagement; phased launch starting with OTC; compliance-by-design; legal counsel | Compliance Lead |
| R02 | Sale of counterfeit or substandard medicines | Safety | 3 | 5 | 15 | High | Strict license verification; source traceability; audits; report-and-suspend workflow | Compliance Lead |
| R03 | Controlled-substance misuse via platform | Safety/Regulatory | 3 | 5 | 15 | High | Exclude/strictly control per regulation; limits; audit; identity checks | Compliance Lead |
| R04 | Data breach of PII / health records | Security | 3 | 5 | 15 | High | Encryption, RBAC, pen testing, monitoring, incident response plan | Security Lead |
| R05 | Low pharmacy/provider adoption | Market | 3 | 4 | 12 | Medium | Onboarding incentives, training, low-friction tools, revenue visibility | Partnerships Lead |
| R06 | Low customer trust/adoption | Market | 3 | 4 | 12 | Medium | Verified badges, ratings, transparent pricing, strong support, marketing | Product/Marketing |
| R07 | Payment provider integration or reliability issues | Technical | 3 | 4 | 12 | Medium | Multiple providers, reconciliation, retries, fallback methods | Engineering Lead |
| R08 | Fayda ID integration unavailable/limited | Technical/Dependency | 3 | 4 | 12 | Medium | Alternate KYC fallback; phased identity requirements | Engineering Lead |
| R09 | Delivery unreliability (coverage, time, spoilage) | Operational | 4 | 3 | 12 | Medium | Partner vetting, SLAs, cold-chain flags, zone-based coverage | Operations Lead |
| R10 | Prescription fraud / forged uploads | Safety/Fraud | 3 | 4 | 12 | Medium | Pharmacist verification, anomaly detection, audit trail | Compliance Lead |
| R11 | Poor connectivity limits usage in regions | Technical/Market | 4 | 3 | 12 | Medium | Lightweight app, offline-tolerant flows, SMS fallback | Engineering Lead |
| R12 | Scalability failures under peak demand | Technical | 2 | 4 | 8 | Medium | Auto-scaling, load testing, capacity planning | Engineering Lead |
| R13 | Cross-border payment/currency friction (diaspora) | Financial | 3 | 3 | 9 | Medium | Supported international methods, clear FX handling | Finance Lead |
| R14 | Provider license expiry causing illegal sales | Compliance | 3 | 4 | 12 | Medium | Automated expiry tracking and auto-suspension | Compliance Lead |
| R15 | Disputes/refund abuse | Financial/Operational | 3 | 3 | 9 | Medium | Clear policies, evidence capture, admin tooling | Operations Lead |
| R16 | Inaccurate inventory causing failed orders | Operational | 4 | 3 | 12 | Medium | Real-time stock sync, re-match logic, penalties for chronic errors | Product Lead |
| R17 | Key-person / talent dependency | Organizational | 3 | 3 | 9 | Medium | Documentation, cross-training, redundancy | CTO |
| R18 | Funding shortfall impacting roadmap | Financial | 3 | 4 | 12 | Medium | Phased MVP, clear KPIs, investor reporting, cost control | CEO/Finance |
| R19 | Competitive entrants | Market | 3 | 3 | 9 | Medium | Speed to market, network effects, provider exclusivity, quality | Product Lead |
| R20 | Third-party service outages (maps/SMS/payment) | Dependency | 3 | 3 | 9 | Medium | Redundant providers, graceful degradation, status monitoring | Engineering Lead |
| R21 | Non-compliance with data-protection law | Regulatory | 3 | 5 | 15 | High | Privacy-by-design, consent, DPO oversight, audits | Compliance/Legal |
| R22 | Reputational damage from safety/quality incident | Reputational | 3 | 5 | 15 | High | Rigorous QA, rapid incident response, transparent comms | CEO/PR |

3. Risk RegisterRisk Score = L x I (1–25). Rating: Low (1–6), Medium (7–12), High (13–19), Critical (20–25).Impact (I): 1 (Negligible) – 5 (Severe)Likelihood (L): 1 (Rare) – 5 (Almost Certain)2. Risk ScoringThis document identifies risks that could threaten the platform's objectives, assesses their likelihood and impact, and defines mitigation and contingency actions with owners. Risks span regulatory, technical, operational, financial, market, and safety domains.1. PurposeStatus: Draft for ReviewPrepared by: Senior Business AnalystVersion: 1.0Product: PharmaLink Ethiopia — Digital Healthcare MarketplaceDocument Type: Risk Analysis & Mitigation PlanPharmaLink Ethiopia — Risk Analysis

Providers are willing to meet verification and data-accuracy obligations.Reliable third-party identity and payment services are available.Regulatory cooperation is achievable with proactive engagement.6. Assumptions Impacting RiskEscalate any risk reaching High/Critical to the steering committee.Assign each risk an owner accountable for mitigation status.Track leading indicators (compliance rate, breach attempts, delivery SLA, dispute rate, adoption).Maintain a living risk register reviewed at least monthly and at each phase gate.5. Risk Monitoring & GovernanceContingency: Re-match, refund policy, provider performance penalties.Preventive: Partner vetting/SLAs, real-time stock sync, cold-chain flags.R09 / R16 — Delivery reliability & inventory accuracyContingency: Incident response plan, breach notification, forensic review, remediation.Detective: SIEM, alerting, audit logs.Preventive: Encryption in transit/at rest, RBAC, least privilege, secure SDLC, pen testing.R04 / R21 — Data breach & data-protection complianceContingency: Immediate suspension, recall notice, regulator notification.Detective: Customer reporting, batch checks, anomaly monitoring.Preventive: Only verified licensed pharmacies; source documentation; periodic audits.R02 — Counterfeit/substandard medicinesContingency: Launch OTC-only and healthcare-service modules first; enable Rx upon approval.Preventive: Engage EFDA/MoH early; co-design compliance controls; pilot under supervision.Trigger indicators: Regulator feedback, policy delays.R01 — Regulatory approval for online Rx sales4. Top Risks — Detailed Response Plans